## Bug & Doc Gap Tracker
ID | Type | Category | Severity | Title | Location / URL | Steps to Reproduce | Actual Result | Expected Result | Impact | Suggested Fix / Improvement | Status
BUG-01 | UI / UX Bug | Documentation | Medium | Scrolling image overlaps API Reference section | https://docs.terminal3.io/t3n/data-owner-guide/data-owner-overview | 1. Open the Data Owner Overview page. 2. Scroll down. 3. Click an image to expand it. 4. Click again to collapse/unclick it. | The image travels upward and overlaps the API Reference section instead of returning to its original position. | The image should animate back smoothly to its original position in the page flow without covering other content. | Broken visual layout disrupts reading and makes the API Reference section inaccessible until the user refreshes. | Fix the image toggle/collapse animation so the element is properly re-inserted into the document flow on close. Use CSS position reflow rather than absolute/fixed positioning. | Open
BUG-02 | UI / UX Bug | Marketing Site | Medium | Hover state hides text inside box on Terminal 3 Insights section | https://www.terminal3.io/ — Terminal 3 Insights section | 1. Go to terminal3.io. 2. Scroll to the 'Terminal 3 Insights' section. 3. Hover the cursor over an image card. | When hovering over an image, the text inside the card/box is hidden (not visible). | Hovering should reveal or keep text visible — either as an overlay or alongside the image. | Users cannot read insight content on hover, defeating the purpose of the interactive cards. | Review CSS hover styles on the Insights cards. Ensure text color or opacity is not set to transparent/0 on :hover. Check for conflicting z-index or visibility rules. | Open
BUG-03 | UI / Navigation Bug | Documentation | Medium | In-page anchor links do not scroll smoothly — URL changes abruptly | T3N > Data Owners Overview > Key Features section | 1. Navigate to T3N Data Owners Overview. 2. Find the 4 Key Features. 3. Click the 'get link' / anchor icon next to any key feature item. 4. Observe page behavior. | The page does not scroll to the section. Instead, the current screen changes to show the clicked keyword abruptly with no smooth scroll. | Clicking the anchor/link icon should smoothly scroll the page to that section and update the URL hash. | Poor UX for sharing specific sections; abrupt jump is disorienting and may cause users to think the page reloaded. | Add scroll-behavior: smooth in CSS. Ensure anchor href targets match correct element IDs. Use JavaScript smooth scroll if CSS alone is insufficient. | Open
BUG-04 | Functionality Bug | Platform / Testnet | High | External links under maintenance — 'Go to network.terminal3.io' and T3N Dashboard inaccessible | T3N > Data Owners > Getting Started | 1. Navigate to T3N Data Owners Getting Started page. 2. Click 'Go to network.terminal3.io'. 3. Also click 'Manage your identity' / T3N Dashboard link. | Both links display an 'Under Maintenance' page. | Both links should open working pages — the T3N network portal and the T3N identity/dashboard respectively. | Developers cannot complete Data Owner onboarding or access identity management, blocking all downstream workflows. | Either restore the services or display a clear maintenance banner on the source page with estimated ETA. Add a maintenance status page link. | Open
BUG-05 | UI / UX Bug | Developer Portal | Medium | Copy API Key button stays in 'Copied' state permanently — never resets | https://www.terminal3.io/claim-page | 1. Complete the token claim process. 2. Click the copy icon/button next to the API key. 3. Wait several seconds. 4. Click the button again. | The button permanently displays 'Copied' state. There is no visual reset, and subsequent clicks give no new confirmation. | Button should show 'Copied' for 2–3 seconds, then revert to 'Copy'. Each click should trigger a fresh copy and show a new confirmation. | Developers may believe key was copied when it wasn't. Especially critical because the API key is shown only once and cannot be retrieved later. | Add a setTimeout() to reset button text/state after ~2500ms. Optionally show a toast notification. Add a 'Download .env' backup option. | Open
BUG-06 | Functionality Bug | Platform / Testnet | High | AI Agent creation form — 'Create' button stays disabled despite valid form | https://testnet.network.terminal3.io/agents | 1. Navigate to AI Agents. 2. Click 'New Agent'. 3. Enter a valid Agent DID. 4. Select an Authorized Contract. 5. Observe Create button. 6. Open DevTools → run document.querySelector('form')?.checkValidity() → returns true. 7. Manually remove disabled attribute from Create button. 8. Click Create. | Create button remains disabled even though form passes validation. Manually clicking after removing disabled attribute produces no action, no success message, and no error. | Create button should enable when form is valid. Clicking it should either create the agent or return a clear validation/error message. | Users cannot complete the AI Agent creation workflow, entirely blocking testing of agent delegation and authorization features. | Debug the JavaScript condition that controls the Create button's disabled state. Ensure form.checkValidity() result actually triggers UI update. Add proper success/error response handling. | Open
BUG-07 | UI / UX Bug | Onboarding / Form Validation / UX | Medium | Changing connected Google account does not reset previously entered form data | https://www.terminal3.io/claim-page | 1. Navigate to the claim page. 2. Sign in using a Google account. 3. Fill in: First Name, Last Name, Industry, Role, Campaign Code. 4. Click the 'Change' link next to the connected email address. 5. Switch to a different Google account. 6. Return to the claim form. | Previously entered form values (First Name, Last Name, Industry, Role, Campaign Code) remain populated after switching to a different Google account. | All user-entered form fields should be cleared and reset when a different Google account is selected, ensuring form data matches the currently authenticated user. | Incorrect user information may be submitted under the wrong account, causing onboarding confusion, data integrity issues, and accidental submission of stale data. | On account change/switch, trigger a full form reset (clear all controlled input state). Bind form field defaults to the authenticated user's session, not component state. | Open
DOC-01 | Documentation Gap | Onboarding | Critical | No self-serve developer signup on terminal3.io — only enterprise sales form exists | https://www.terminal3.io — All navigation links | 1. Go to terminal3.io. 2. Click every button and navigation link looking for 'Sign Up', 'Get Started', or 'Developer Portal'. 3. All paths lead to a 'How can we help?' enterprise contact form. | No developer-specific signup path exists on the main website. The only way to reach the developer claim page is via the direct URL terminal3.io/claim-page, which is undiscoverable. | A 'Developer Sign Up' or 'Get API Key' button should be visible on the main website, leading directly to the claim page or developer portal. | HIGH — New developers discovering Terminal 3 organically will hit a dead end. The developer onboarding funnel is completely broken for organic traffic. | Add a prominent 'Start Building' or 'Get API Key' CTA in the main navigation that links to the claim/developer portal page. | Open
DOC-02 | Documentation Gap | Onboarding | Critical | No clear developer onboarding flow on main website | https://www.terminal3.io | 1. Visit terminal3.io as a new developer. 2. Try to find: how to create an account, get API credentials, access sandbox, register a DID, access SDK docs. | No unified 'Getting Started' flow exists. Each item requires independent discovery across multiple pages. | A dedicated 'Getting Started' page covering: account creation, sandbox token claim, API key retrieval, DID registration, and first API call example. | New developers spend significant time searching for basic setup instructions before they can start building. | Create a dedicated Getting Started / Quick Start page with numbered steps covering the full initial setup sequence. | Open
DOC-03 | Documentation Gap | Developer Experience | High | DID registration requirement not clearly explained in onboarding | Onboarding docs / API reference | 1. Complete onboarding. 2. Attempt to use VC endpoints with just the API key. 3. Receive error: 'T3N API key not authorized for DID/VC endpoints. Register the DID first.' | Error appears with no prior warning that DID registration is a mandatory prerequisite. The onboarding flow does not mention this requirement. | Onboarding should clearly state that a DID must be registered before VC operations, and that the API key alone is not sufficient. | Developers may incorrectly assume the API key is invalid or the SDK is malfunctioning, leading to wasted debugging time. | Add a prerequisite callout box before VC API docs: 'Before using VC APIs, you must register a DID.' Link to the DID registration page. | Open
DOC-04 | Documentation Gap | Developer Experience | High | Placeholder DIDs silently cause integration failure — no warning in docs | VC/DID documentation | 1. Follow docs to integrate VC features. 2. Use a placeholder DID like 'did:key:my-agent' or 'did:key:phoenix-agent-001'. 3. Observe application behavior. | Application silently fails or falls back to simulation mode. No error clearly indicates the DID is invalid. | Documentation should prominently warn that DIDs must be cryptographically generated and arbitrary strings are not valid DIDs. | Applications silently fall back to simulation mode, leading developers to believe integration is working when it isn't. | Add a warning box in DID docs: 'Do not manually create DIDs. Generate them using the VC SDK.' Include a code example. | Open
DOC-05 | Documentation Gap | Developer Experience | High | DID generation flow is not discoverable — full key generation chain not documented on registration page | DID Registration documentation page | 1. Navigate to DID registration page. 2. Follow instruction: 'Please refer to our VC SDK'. 3. Try to find the correct generation sequence. | The page does not show that developers must call: randomKeyBls() → blsG2PublicKeyFromPrivateKey() → bbsDidFromPublicKey() before registering a DID. | The full DID generation example should be directly on the DID registration page, not buried in a separate SDK reference. | Developers incorrectly assume DID registration creates the DID for them, causing repeated registration failures. | Include the complete DID generation code example (all 3 steps) directly on the DID registration documentation page. | Open
DOC-06 | Documentation Gap | Developer Experience | High | No end-to-end integration example covering full VC workflow | Docs — VC/DID API reference | 1. Attempt to build a complete VC workflow: key gen → DID gen → DID register → issue VC → store VC → generate proof → verify proof. 2. Follow individual API docs for each step. | Documentation covers individual APIs in isolation. No complete tutorial project exists that chains all steps together. | A complete end-to-end tutorial project showing all 7 steps in sequence with working code. | Developers must piece together multiple documentation pages, significantly increasing onboarding time and error rate. | Publish a complete tutorial project (e.g., on GitHub) with inline comments covering the full 7-step VC workflow. | Open
DOC-07 | Documentation Gap | Developer Experience | Medium | Wallet address source for DID registration is unclear | DID Registration API reference | 1. Attempt DID registration: POST with {"did": "...", "wallet_address": "0x..."}. 2. Try to determine where the wallet_address value should come from. | Documentation does not explain whether the wallet address is generated automatically, linked to the developer account, or must be self-managed. | A dedicated explanation clarifying the wallet_address field: its source, whether it is auto-generated, and how to obtain it. | Developers cannot confidently complete DID registration, creating a blocking step in onboarding. | Add a 'Wallet Address' explanation section to the DID registration docs. Clarify source and provide an example or generation guide. | Open
DOC-08 | Documentation Gap | Developer Experience | Medium | API error messages lack actionable guidance — no links or endpoint hints | Staging API — error responses | 1. Make an API call without a registered DID. 2. Observe the error message returned. | Error returns: 'T3N API key not authorized for DID/VC endpoints. Register the DID first.' — with no registration endpoint, payload example, or docs link. | Error should say: 'DID not registered. Register via POST /v1/did/register. See docs: [link]' — contextual and actionable by HTTP status code. | Developers spend unnecessary time searching for the right registration endpoint instead of being directed there immediately. | Update error responses to be context-aware: 401 → auth failure message, 404 → DID not found + registration link, 403 → permission scope message. | Open
DOC-09 | Documentation Gap | Developer Experience | Medium | No way to determine if SDK requests are live vs. simulated | SDK integration / docs | 1. Integrate the Terminal 3 SDK. 2. Make API calls. 3. Try to determine if requests are hitting live services or returning simulated responses. | No health-check endpoint or integration verification mechanism exists. SDK may silently return mocked responses. | A health-check endpoint and integration verification guide to confirm live connectivity and successful DID registration. | Developers may believe integration is working when all responses are mocked, leading to broken production deployments. | Provide a GET /health or GET /v1/status endpoint. Document how to verify live vs. simulated mode. Add an integration checklist. | Open
DOC-10 | Documentation Gap / Auth Bug | Onboarding / Authentication | Medium | Misleading DID error masks actual 401 authentication failure | staging.terminal3.io — GET /v1/did | 1. Visit Agent Developer Kit claim page. 2. Complete onboarding and copy the API key. 3. Run: curl -X GET https://staging.terminal3.io/v1/did -H 'x-api-token: <claimed_api_key>' 4. Observe response. | 401 Unauthorized returned. SDK/error directs developer to DID registration, but root cause is API key rejection — not missing DID. | Either 200 OK (DID found) or 404 Not Found (no DID yet). Error message should identify authentication failure, not DID registration. | Developers waste hours debugging DID generation and registration when the actual issue is an invalid/inactive API key. | Return contextual errors by HTTP status. For 401: 'Authentication failed. Verify x-api-token.' Add an API key validation step during onboarding. | Open
DOC-11 | Documentation Gap | Onboarding / Authentication | Medium | Claimed API key returns 401 against documented endpoint — key may not be immediately active | staging.terminal3.io — GET /v1/did | 1. Complete onboarding and claim API key from Agent Developer Kit page. 2. Use key as x-api-token header. 3. Call GET https://staging.terminal3.io/v1/did. 4. Observe 401. | 401 Unauthorized: {"errors":[{"code":"unauthorized","message":"Unauthorized request."}]} | 200 OK or 404 depending on DID status. Documentation should clarify if claimed key needs additional activation. | Significant onboarding confusion: claim page says 'Copy your API key and start building' but key is rejected by documented endpoint. | Clarify whether claimed key is the x-api-token or if additional steps are needed. Provide an API key verification step in onboarding. Improve error specificity (invalid token vs inactive vs wrong environment). | Open
DOC-12 | Documentation Gap | Documentation / Developer Onboarding | Medium | Endpoint documentation inaccurate or incomplete — team confirmed docs being updated | docs.terminal3.io — Agent Auth SDK / DID endpoints | 1. Follow available documentation to implement DID lookup/authentication flow. 2. Attempt API calls using documented endpoints. 3. Receive authentication failures. 4. Contact support for clarification. | Terminal 3 team responded: 'Please give us a few moments to update the docs to ensure all the endpoints are accurate.' — confirming docs were stale. | A complete, accurate, and versioned API endpoint reference clearly separating production, staging, and sandbox environments. | Developers integrate against incorrect endpoints, receive 401 errors, and spend hours debugging valid code due to stale docs. | Publish a definitive endpoint reference with environment URLs. Add a health-check endpoint. Include a complete Agent Auth integration example. Implement automated link/endpoint validation in CI. | Open
DOC-13 | Documentation Gap | Documentation / Broken Link | Low | Introduction documentation page returns 404 | https://docs.terminal3.io/t3n/overview/introduction | 1. Open https://docs.terminal3.io/t3n/overview/introduction 2. Observe the response. | 404 Page Not Found | The Introduction page loads and provides onboarding/introduction information for new developers. | New developers following documentation navigation hit a dead end at the first page, reducing confidence in the docs. | Restore the missing page or redirect the URL to the correct location. Add automated link validation to the documentation deployment pipeline. | Open
DOC-14 | Documentation Bug | Documentation | Medium | Product Releases page renders 'null' — no changelog or version history displayed | https://docs.terminal3.io/releases/product-releases.md | 1. Open the Product Releases page URL. 2. Wait for the page to load. 3. Observe content. | Page displays only the text 'null'. No release information, changelog, redirect, or error explanation is provided. | A changelog or product release history page with version notes. | Developers cannot access release notes or version history and may miss breaking changes to APIs or SDK behavior. | Fix the CMS/markdown rendering pipeline for this page. Populate with at least a placeholder release note. Add monitoring for null-content pages. | Open
DOC-15 | Documentation Gap | Documentation | Critical | ADK Overview does not explain what an 'Ethereum wallet' is or how to create one | https://docs.terminal3.io/developers/adk/overview/what-is-adk | 1. Read the ADK Overview page. 2. Find: 'One call signs in with your Ethereum wallet'. 3. Search entire documentation for how to create or connect an Ethereum wallet. 4. Find zero guidance — no link, no explanation, no recommended tool. | Documentation assumes the reader already has an Ethereum wallet and knows how to use it. No mention of MetaMask, WalletConnect, or any other wallet option anywhere in ADK docs. | A clear explanation of what an Ethereum wallet is, how to create one (e.g., MetaMask), and how to connect it to the T3N SDK. Beginner developers should not need prior Web3 knowledge. | CRITICAL — The very first step of SDK authentication requires an Ethereum wallet. Developers without Web3 background (the majority of AI/backend developers) are immediately blocked with no guidance. | Add a 'Prerequisites' or 'Web3 Wallet Setup' section to the ADK Overview. Recommend MetaMask or WalletConnect with a setup link. Include a short explanation of what an Ethereum wallet is in the context of T3N. | Open
DOC-16 | Documentation Gap | Documentation | Critical | ADK Overview does not explain what 'fuel' is or how to estimate costs before building | https://docs.terminal3.io/t3n/how-t3n-works/tee-contracts.md — Fuel section | 1. Read the TEE Contracts page. 2. Find: 'Each contract invocation is assigned a bounded computation budget (fuel)'. 3. Search docs for: fuel cost per operation, how to estimate fuel, what happens when fuel runs out, how to get more fuel. 4. Find no pricing table, no cost estimator, no fuel consumption guide. | The claim page states 20,000 tokens allow 'roughly 5,000 protected actions' but documentation never explains the fuel model, consumption rates, or how to optimize for fuel efficiency. | A fuel cost table showing approximate consumption per operation type (e.g., 'simple key-value read = 10 fuel', 'HTTP POST call = 500 fuel'). Also needed: what happens when fuel is exhausted mid-execution. | CRITICAL — Developers cannot plan or budget their applications without understanding costs. A developer could exhaust all test tokens in minutes without realizing it. | Publish a fuel cost reference table. Document what happens on fuel exhaustion (error thrown vs silent fail). Add a fuel estimation guide or calculator. Surface remaining fuel balance in the developer dashboard. | Open
DOC-17 | Documentation Gap | Documentation | Critical | No Rust-to-WASM contract development guide — docs jump from concept to 'publish' with zero implementation steps | https://docs.terminal3.io/developers/adk/overview/what-is-adk — Contracts section | 1. Read ADK Overview: 'publish a Rust-to-WASM contract'. 2. Search docs for Rust setup instructions, WASM compilation guide, Cargo.toml configuration, or example contract templates. 3. Find zero guidance on any of these topics. | The only code example is conceptual pseudocode on the TEE Contracts page. No working example, no repository link, no compilation command, and no Rust project template exists. | A 'Writing Your First TEE Contract' guide covering: Rust toolchain setup, project structure, WASM compilation command, how to publish the compiled binary, and a minimal working example. | CRITICAL — Writing Rust-to-WASM contracts is a non-trivial skill. The documentation jumps from 'here is what contracts can do' to 'publish your contract' with zero implementation guidance. Most developers will be completely blocked. | Publish a step-by-step 'First TEE Contract' tutorial with: Rust + wasm-pack setup, project template, Cargo.toml config, compilation command, and a minimal end-to-end working example. Link a GitHub starter repo. | Open
DOC-18 | Documentation Gap | Documentation | Medium | Delegate Access page has two 'Coming Soon' sections with no timeline or workaround | https://docs.terminal3.io/t3n/data-owner-guide/delegate-access.md | 1. Navigate to the Delegate Access documentation page. 2. Scroll to 'Delegate Access to Human Users' section — reads: 'Coming soon.' 3. Scroll to 'Delegate Access to Third-Party Services' section — reads: 'Coming soon.' | Both 'Delegate Access to Human Users' and 'Delegate Access to Third-Party Services' sections exist in the docs with no content — only 'Coming soon.' No timeline, no workaround, no alternative approach. | Either complete documentation for these features, or provide a clear timeline for availability, or a note explaining they are not yet available in the sandbox with a suggested workaround. | MEDIUM — Developers building applications requiring these delegation types (most enterprise use cases) have no way to plan around these limitations. | Replace bare 'Coming soon.' with a structured placeholder: feature status, estimated timeline (even a quarter), known workarounds, and a link to subscribe for updates or changelog. | Open
DOC-19 | Documentation Bug | Documentation | Medium | Manage Identity and Introduction pages contain dead image code — screenshots permanently hidden via {false && ...} | https://docs.terminal3.io/t3n/data-owner-guide/manage-identity.md — also Introduction page | 1. Navigate to the Manage Identity documentation page. 2. View the raw markdown/JSX source. 3. Find the block: {false && ( <> [img: profile-light.png] [img: profile-dark.png] )} 4. Confirm images are permanently hidden. Same pattern appears on the Introduction page. | Documentation contains commented-out image blocks using {false && ...} — a JSX pattern that permanently prevents the images from rendering. Users who rely on visual documentation see no screenshots. | Either display the profile interface images (light and dark mode) to help users understand the dashboard UI, or remove the dead code entirely. | MEDIUM — Hidden images reduce documentation quality for visual learners. Dead code also indicates incomplete documentation that was never finished. | Remove the {false && ...} wrapper to render the images, or delete the dead code blocks entirely. Add automated linting to detect permanently-false conditional renders in documentation source. | Open